## Bugs
Project | Issue Type | Bug ID | Summary | Priority | Severity | Status | Components | Affects Version | Fix Version | Environment | Module | Feature | Test Case ID | Reproducibility | Reporter | Assignee | Labels | Linked Requirement | Description | Created
Manual QA Case Study - Ambulance | Bug | BUG-AMB-001 | Out-of-coverage address accepted and dispatched | Critical | Blocker | Open | Coverage | 1.0.0 |  | Staging · Chrome 120 · Windows 10 | Coverage | Out of Area | AMB-060 | Always | Tanzid | Unassigned | portfolio, ambulance, blocking | REQ-AMB-COVER | Steps: 1) Enter drop outside service zone Expected: Clear rejection message Actual: Booking confirmed; later auto-cancels | 2025-10-03
Manual QA Case Study - Ambulance | Bug | BUG-AMB-002 | Location permission denied does not show manual entry | High | Major | Open | Location | 1.0.0 |  | Staging · Android Chrome 126 | Location | Permissions | AMB-005 | Always | Tanzid | Unassigned | portfolio, ambulance, ux | REQ-AMB-LOC | Expected manual address fallback when permission denied; actual: stuck on spinner. | 2025-10-03
Manual QA Case Study - Ambulance | Bug | BUG-AMB-003 | ETA not refreshing; stays static >5 minutes | Medium | Major | Open | Quote/ETA | 1.0.0 |  | Staging · Firefox 118 · Ubuntu | Quote/ETA | ETA | AMB-020 | Sometimes | Tanzid | Unassigned | portfolio, ambulance, eta | REQ-AMB-ETA | Expected periodic ETA refresh every 60s; actual: no change for >5m. | 2025-10-03
Manual QA Case Study - Ambulance | Bug | BUG-AMB-004 | ICU type selection hidden on 1366×768 viewport | Low | Minor | Open | Fleet | 1.0.0 |  | Staging · Edge 120 · Windows 11 | Fleet | Type Selection | AMB-010 | Always | Tanzid | Unassigned | portfolio, ambulance, ui | REQ-AMB-FLEET | UI truncation hides ICU radio; cannot scroll to reveal. | 2025-10-03
Manual QA Case Study - Ambulance | Bug | BUG-AMB-005 | Spam booking not throttled at 10 req/10s | High | Major | Open | RateLimit | 1.0.0 |  | Staging · Chrome 120 · macOS 13 | RateLimit | Spam | AMB-050 | Always | Tanzid | Unassigned | portfolio, ambulance, security | REQ-AMB-RATE | Expected 429 with cooldown message; actual: multiple bookings created. | 2025-10-03
Manual QA Case Study - Ambulance | Bug | BUG-AMB-006 | Cancellation policy text contradicts FAQ | Medium | Minor | Open | Booking | 1.0.0 |  | Staging · Chrome 120 · Windows 10 | Booking | Cancel | AMB-040 | Always | Tanzid | Unassigned | portfolio, ambulance, policy | REQ-AMB-CANCEL | UI says 'free within 15m'; FAQ says 'free within 10m'. | 2025-10-03
Manual QA Case Study - Ambulance | Bug | BUG-AMB-007 | Confirm button enabled with missing phone number | High | Major | Open | Booking | 1.0.0 |  | Staging · Android Chrome 126 | Booking | Confirm | AMB-030 | Always | Tanzid | Unassigned | portfolio, ambulance, validation | REQ-AMB-BOOK | Form validation bypass allows empty phone; booking still created. | 2025-10-03
Manual QA Case Study - Ambulance | Bug | BUG-AMB-008 | Map pin reversed (pickup/drop swapped) after edit | Medium | Major | Open | Location | 1.0.0 |  | Staging · Firefox 118 · Ubuntu | Location | Pickup/Drop | AMB-001 | Sometimes | Tanzid | Unassigned | portfolio, ambulance, map | REQ-AMB-LOC | Editing drop address swaps pin colors; leads to wrong dispatch. | 2025-10-03

## HowToUse
Field | Guidance
Summary | One-line problem statement
Priority | P1=Highest, P4=Low (use High/Medium/Low here)
Severity | Blocker/Critical/Major/Minor/Trivial
Components | Functional area of the app
Affects Version | Version under test (e.g., 1.0.0)
Environment | OS/Browser/Device
Module | Module name matching test assets
Feature | Feature name matching test assets
Test Case ID | Cross-reference to TEST_CASES.csv
Reproducibility | Always/Sometimes/Rarely
Labels | Comma-separated keywords
Linked Requirement | Map to RTM requirement ID
Description | Include Steps, Expected, Actual in bullet form